## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I catch CoViD | 3 | 40 | 120 | 2021-01-14 | Mitigated | M | learned instructor has extension possible
equipment stops working | 5 | 20 | 100 | 2021-01-14 |  | O | make sure everythings working, check up often
Busy with other classes | 70 | 40 | 2800 | 2021-03-23 |  | O | Lay out schedule of rest of semester for all classes/make plan
will get stuck/don't know how to move on | 40 | 20 | 800 | 2021-03-23 | Mitigated | M | attend office hours/talk to classmates
unable to attend offices hours | 70 | 13 | 910 | 2021-03-23 | Resolved | R | (see row 5) contact TA/John via Slack
unclear of instructions | 20 | 40 | 800 | 2021-03-23 |  | O | start making diagrams/ask for help if problems or holes found
Physics model difficulties | 70 | 40 | 2800 | 2021-04-21 |  | O | trouble moving objects on LCD screen, seek help

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100